## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #1
Create random addresses | 9 | Alex Espino | Active | 8 | DAY 1: 1; DAY 2: 0.5; DAY 3: 4; DAY 4: 1; DAY 5: 1
Read addresses and add to Priority Queue | 5 | Kimberly Miller | Active | 6 | DAY 1: 1; DAY 2: 2; DAY 3: 4; DAY 4: 3; DAY 5: 1
Print neghborhood | 7 | Abdullah Alramyan | Active | 9 | DAY 1: 1; DAY 2: 1; DAY 3: 3; DAY 4: 7; DAY 5: 8
User Story #2
Generate Order Time | 7 | Alexander | Active | 8 | DAY 1: 5; DAY 2: 2; DAY 3: 4; DAY 4: 2; DAY 5: 1
Modify Priority Queue | 7 | Alexander | Active | 15 | DAY 1: 5; DAY 2: 3; DAY 3: 1; DAY 4: 0; DAY 5: 0
Compute route truck must follow | 9 | Kimberly | Active | 20 | DAY 1: 6; DAY 2: 4; DAY 3: 4; DAY 4: 4; DAY 5: 1
Display Simulation | 8 | Abdullah |  | 8 | DAY 1: 1; DAY 2: 0.5
User Story #3
Resize the neighborhood | 5 | Riley | Complete | 4 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Implement 2nd route strategy | 7 | Kimberly | Complete | 20 | 2 | 2 | 4 | 4 | 3 | 2 | 1 | 1 | 0 | 0
Add food order to random addresses | 5 | Riley | Complete | 2 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor what we had after last sprint to be more general | 10 | Riley | Complete | 15 | 0 | 0 | 4 | 8 | 6 | 1 | 0 | 0 | 0 | 0
Update Requirements | 2 | Kimberly | Complete | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
UML |  | Abdullah
Compare the cost effectiveness of routing methods |  | Abdullah
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 118 | 23 | 15 | 30.5 | 30 | 22 | 3 | 1 | 1 | 1 | 1 | 0